## Sheet1
No roadblock
Waiting on text
Waiting on implementation
0 - required for hand-in
1 - raises marks significantly
2 - raises marks slightly
3 - little effect but nice to have
Priority (0-3) | Location | Task | Completion
2 | Literature Review | Reorganise automated reconfiguration section
3 | Literature Review | Add key technologies I will use
1 | Literature Review | Edit gaps and opportunities
0 | Draft | Write Abstract
1 | Draft | Write Acknowledgements
1 | Draft | Write Project Scope
1 | Draft | Edit Software Design and Development
0 | Draft | Write Software Design - Motion planning section
0 | Draft | Write Software Design - Feedback strategies section
0 | Draft | Write implementation - state queue class
0 | Draft | Write implementation - state class
0 | Draft | Write implementation - module class
0 | Draft | Write implementation - motion planning
0 | Draft | Write implementation - feedback strategy
0 | Draft | Write testing and results - testing method
0 | Draft | Write testing and results - performance metric
0 | Draft | Write testing and results - analysis of results
0 | Draft | Write discussion - interpretation of results
0 | Draft | Write discussion - comparison to existing work
0 | Draft | Write discussion - implications
2 | Draft | Expand Project Management Procedures section
2 | Draft | Expand Project Management Reflection section
2 | Draft | Write Risk assessment
0 | Draft | Write evolution of project plan section
3 | Draft | Mention discovered problem in last week to management reflection section
0 | Draft | Write Conclusion
0 | Draft | Write Further Work section
3 | Software - Logic | Convert matrix data structure to dictionary to improve memory
2 | Project Planner | Update planner
1 | Software - Physical | Create basic motion planner
2 | Software - Physical | Create advanced motion planner
1 | Software - Logic | Create graph trimming function
0 | Software - Main | Implement feedback strategies
1 | Software - Logic | Commenting
1 | Software - Physical | Commenting
1 | Software - Main | Commenting
2 | Software - Physical | Manipulator base location planning
3 | Software - Logic | Make matching modules by ID an option
1 | Draft | Explain module matching by colour is a replacement for matching by type
Finish writing tasks for software portion